## Guidelines
Guidelines to completing the sheet
1 | All the fields highlighted in yellow | needs to completed manually
2 | Each sheet contains and indication on the top whether the data needs to be filled as per release or per the whole application
3 | Copy the charts from the each of the corresponding sheets. (The summary page is a Sample only)
4 | Alter the chart sizes to fit the email. Please use the sample email for reference.

## Summary Report
Build Quality Indicators
Project: Auto Stream Application
Build Version:
1. Test Execution Results
Module | TC | Passed | Failed | Blocked | Not Executed
Admin Portal | 73 | 72 | 1 | 0 | 0
Seller Portal | 42 | 41 | 1 | 0 | 0
Buyer Portal | 21 | 19 | 2 | 1 | 1
Total | 136 | 132 | 4 | 1 | 1
Test Execution Status (Full) (%) |  | 97.0588 | 2.9412 | 0.73529 | 0.73529
Test Execution Status(Executed) (%) | 137 | 96.3504 | 2.9197 | 0.72993
Executed Test Passed Ratio | 96.35% |  |  |  |  | Total Test Passed Ratio |  | 97.06%
2. Defect Status - Summary View
Defect Status
QA Review | Open Defects | # of Closed Defects | Severity |  |  |  |  | Defect Type
|  |  | Critical (1) | High (2) | Medium (3) | Low (4) | Severity Index | Funtionality | UX | Security/Performance | Control
QA Review #1 | 14 | 0 | 2 | 7 | 0 | 5 | 2.43 | 5 | 0 | 2 | 7
3.Defect Severity Index
3. Reccomendation | Partial Go |  |  |  | Go
No Go
4.QA Lead's Comment | This application is better to release after fixing the defects that mentioned in the Defect Tracking Sheet.

## Test Execution Status
** To be considered for the particular release
Module | TC | Passed | Failed | Blocked | Not Executed
A | 8 | 1 | 6 | 1 | 0
B | 4 | 1 | 1 | 2 | 0
C | 37 | 31 | 3 | 3 | 0
D | 44 | 4 | 33 | 0 | 7
E | 70 | 59 | 11 | 0 | 0
Total | 163 | 96 | 54 | 6 | 7
Test Execution Status (Full) (%) |  | 58.9% | 33.13% | 3.681% | 4.294%
Test Execution Status(Executed) (%) | 156 | 61.54% | 34.62% | 3.846%

## Defect Status Distributions
** For the whole application
Defect Status
| QA Review | Open Defects | # of Closed Defects | Severity |  |  |  |  | Defect Type
|  |  |  | Critical (1) | High (2) | Medium (3) | Low (4) | Severity Index | Funtionality | UX | Security/Performance | Control
| QA Review #1 | 64 | 0 | 1 | 11 | 37 | 16 | 2.67 | 39 | 9 | 4 | 12
| QA Review #2 | 61 | 36 | 0 | 8 | 61 | 20 | 2.64 | 35 | 12 | 28 | 14
| QA Review #3 | 18 | 52 | 0 | 1 | 42 | 12 | 2.58 | 15 | 3 | 28 | 9
| Total | 143 | 88 | 1 | 20 | 140 | 48 |  | 89 | 24 | 60 | 35

## Defect Serverity Index
** For the whole application
Severity Index Calculation
Serverity | Weight
Blocker (L1) | 4
Major (L2) | 3
Minor (L3) | 2
Cosmetic + Trivial (L4) | 1
Application Defect Serverity Index (DSI) Calculation
QA Review | 1
Equation | [ (No.of L1 Defects x L1 Weight) + (No. of L2 Defects x L2 Weight) + (No. of L3 Defects x L3 Weight) + (No. of L4 Defects x L4 Weight) ]
Total Open Defects
No. of Blocker | 1
No. of Major | 1
No. of Minor | 1
No. of Trivial + Cosmetic | 1
Total Open Defects | 4
Defect Severity Index (DSI) | 2.5
Minimum No. of Build Cycles Expected | 2.5
(Note : This means 1- 2 builds can be expected for closed more than 80% of defects.)
Standards :
a) Need minimum 0.5 Defect Serverity Index ratio to UAT release with 0 known issue (Best Case)
b) Need to reach 1.0 Defect Serverity Index ratio to decide UAT release with known issues. (Conditional GO)
c) The Defect Severity index is sloping down consistenly. This indicates an increasinglyfavorable trend. As the test cycle progresses (from cycle 1 to cycle n). the Severity index is sloping which suggests increasing quality of the application.
d) According to best scenario, Dev team can be reduce only 1.0 within eachbuild iteration from previous DSI figure
E.g.
Hydro One :

## Defect Density
** For the whole application
Measure / Metric Name ==> | Defect Density
Definition | Number of defects (including the review comments and test defects, both internal and client reported) per KLOC of the code developed
Metric Category | Quality
Unit of Measure | Defects / KLOC
Frequency of Data Analysis / Reporting | Weekly during Construction phase
Data 1 | Number of defects
Data 2 | Size in LOC
Computation Formula | Number of defects / KLOC
Purpose | To understand the Quality of the code and to estmate the number of defects that could be expected in remaining period of coding
How to use | This information is useful to estimate the possible number of defects based on the size of the projects and focused attempts can be made to uncover as many defects, preventing them from being delivered to the client
Application Size in KLOC | 1
Number of Open Defects | 2
Defect Density | 2
QA Review Cycle | Defect Density
1 | 1
2 | 2
3 | 3
4 | 4
5 | 4
6 | 6

## Defect to Remark Ratio
** To be considered for the particular release
Measure / Metric Name ==> | Defects to Remarks Ratio
Definition | Ratio of number of Defects (Remarks accepted as Defects by the development team) to the total number of Remarks raised by the Test Team, computed after each round of testing
Metric Category | Efficiency
Unit of Measure | %
Frequency of Data Analysis / Reporting | After each round of testing
Data 1 | Number of remarks accepted as defects
Data 2 | Number of Remarks logged
Computation Formula | (Number of remarks accepted as defects * 100 ) / Number of Remarks logged
Purpose | To understand, analyze and exercise better control over the defects reported by the testers
How to use | Lesser value of this metric indicates greater need for training the test team on domain and project specific information. Detailed analysis can provide other inputs for making necessary decisions in enhancing this value thus saving effort and time for the test and development teams
| Total Number of Remarks | 1
| Total Number of Remarks accepted as defects | 1
| Defect to Remark Ratio | 100%
QA Review Cycle | Defect to Remark Ratio
1 | 1
2 | 0.5
3 | 0.3
4 | 1
5 | 1
5 | 1